## Mandays Development
Module | List Module | Activity/Detail Module | Notes | Mandays
User Admin | User Management | Create User (User Name, User Login, Password) | 2 | 4
|  | Update User | 1
|  | Delete User | 1
| Data Management | Data Bank (Integration get from control bank) | 5 | 15
|  | Data GL (Integration API) | 5
|  | AR & AP (Integration) | 5
Form | Landing Page | Select box (Select Bank) | 1 | 16
|  | Grid Table | 2
|  | Button Upload | 3
|  | Button Edit | 3
|  | Button Cancel | 3
|  | Button Post (Integration UiPath) | 4
| Bank Reconciliation | Label Bank account | 1 | 28
|  | Date Picker | 1
|  | Bank Statement: - Grid table - Button bank Charge - Button bank income | 3
|  | Bank charge entry box | 3
|  | bank income entry box | 3
|  | Epicor Unreconciled: - Grid table (Integration with API) - Button reconcile (Logic action consume data) | 4
|  | Reconciled Entries: - Grid table (Matching data) | 3
|  | Button reverse | 3
|  | Opening balance | 3
|  | Closing balance calculation | 1.5
|  | Statement Closing | 1
|  | Variance calculation | 1.5
63

## Mandays SDLC
Activity | Result Document | Total PIC | Total Mandays
Testing/UAT | Test script | (SA/QA) | 3
Documentation | Design, define & deployment | (SA/QA) | 5
Deployment | Deploy production | 2 (Developer & PM/QA) | 1
Closing | Review project | PM & SA/QA | 1
10
Notes:
Documentation standard Itasoft